## S#1BL
Priority → | Sprint 1 Back Log | Assigned? | Due Date | Progress | Notes
| Complete Sprint Overview Video by September 11 |  | 2014-09-11
| Prioritize backlog & Finish sprint backlog | Ethan | 2014-09-09 | Done
| Coordinate with the EE majors to get their task list for our video | Ethan | 2014-09-09
| Get a Windows box from Sam Lee to run Open PDC on | Chad & Ethan | 2014-09-04 | Requested | (Ask CPT Spruce for an RT Request)
| Create and initial set of user stories | Quintin
| Create 60 Elevator speech for video | Mike | 2014-09-09 |  | Needs to include 5w's of the project and what we plan to do
| Create a preliminary network diagram | Chad | 2014-09-09
| Write a work diary | Chad | 2014-09-09
Create relational schema
Active Domain Preparation Planned
C# Refresher and practice as a group (design a simple GUI)
How to create graphics from the database
Questions for Project Owner
| 1.Could PO put in a RT request for windows box? |  |  | Done | Doing it
| 2.What format does the user stories need to be in? |  |  | Done | Look at the lesson slides
| 3.What network specifications are there for the capstone? |  |  | Done | Likely no need for arouter but PO still doesn’t know
4.What criteria would the user look for/what will the user look for in the database?