## S#2PBL
Priority → | Sprint 2 Back Log Blood sprint* *Our blood courtesy of LTC Lanham | Assigned? | Due Date | Progress | Hours | Expected Hours | Notes
| Finish Setting up Open PDC | Chad & Mike | 2014-10-04 | Installed | 3 | 1 | Installed but was delayed. We're having trouble working out the connection format of the open PDC to our PMUs
| Create a prototype GUI | Quintin & Ethan | 2014-10-04 | Completed on another computer | 5 | 3 | Install in progress but delayedbecuase of the computer delays | n
| Set Up DHCP | Chad & Mike | 2014-10-04 | On HDD | 0 | 3 | Install in progress but delayed
| Install SQLServer on our system | Quintin & Ethan | 2014-09-24 | Installed | 2 | 1 | Installed but was delayed. Compatibility issue with AGM version of windows used by USMA. We had to get a plan version of windows installed. Chad has been studying the functions of SQL server since its relatively new to all of us.
| Install Visual Studio on our system | Quintin & Ethan | 2014-09-26 | On HDD | 2 | 1 | Will Install but was delayed
| begin working with the Routing Protocol | Chad & Mike | 2014-10-04 |  |  | 2 | We havent gotten to this since the computer issues have delayed us.
| Build a provisional databse in SQL Server | Quintin & Ethan | 2014-10-04 |  | 1 | 4 | We're going to make the interim on another computer just for farmiliarization with the SQL server syntax and format
| Turn on the Grid and use Wireshark to view data |  | OTF | Complete | 4 | 0 | Wireshark has been capturing data but we've had some trouble capturing UDP packets
| Create relational schema | chad | 2014-10-04 | tentative | 1 |  | Chad created this but it doesn’t have the securoity information added yet
| Organize Wiring |  | 2014-10-04 |  |  |  | We rewired it to be better organized and work with out laptop better
| Build a provisional GUI in Visual Studio | Quintin & Ethan | 2014-10-04 |  | 2 |  | Gui is created on the desktop without any links to a database. It's really just a temporary design but hopefully we can transfer it over.
| Active Domain Preparation | Chad & Mike | 2014-09-11
| Create Network Diagram | Chad | 2014-09-11 | Done | 1
| Remake backlog | Ethan | 2014-10-04 | Done | 0.5 | 1 | Here are the hours we spent, We didn’t expect these things, here are the things that we had planned but couldn’t complete. Show a design and finalized schematic of the grid design.
| How to create graphics from the database |  | 2014-10-24
| Class Instruction Time | ALL |  | 1 of 2 | 0
| Plan Sprint goal W/ CPT Spruce | ALL | 2014-09-17 | Complete | 4 |  | Our orignal goal was changed to a much more tenacious one. Capture, store, and display was the new one.
| Set up computer workstation and wiring | Ethan |  | Complete | 1 |  |  |  | Make a write up of the things that were holding us up.
| Meet with the Test Bed Installers (Ask Questions) | ALL | 2014-09-11 | Complete | 8
| C# Refresher and practice using Ethan's old project | Quintin & Ethan | 2014-09-11 |  | 1 |  | Complete
| PLANNING & GOAL SETTING |  | 2014-10-04 |  | 4 | 8
| Smart Grid orientation | Quintin | 2014-10-04 |  |  | 2
| Plan sprint 2 video | ALL | 2014-10-04 |  |  | 2
| Build picture of grid for the GUI | Ethan | 2014-10-04
| Film video | ALL | 2014-10-04 |  |  | 2
| Create SQL Server Database | ALL | 2014-09-30 | DELAYED |  | 3 | The install process has blocked us from completing this in time. Chad has been studying it but hasn’t been able to get it ready
| Get tripod and filming gear for Sprint 2 video | Ethan | sss
| Create provisional SQL database |  | 2014-10-04 | DELAYED |  |  | The install process has blocked us from completing this. Chad has been studying it to make one on his computer
| Email Nick (The IT guy for the grid) | Mike | 2014-10-03 | Emailed |  | 0.2
| Create GUI | Quintin & Ethan | 2014-12-10
| Set up the server | Chad & Mike | 2014-12-10
[5 empty] | 39 | 33.2
Done
| Get a Windows box from Gaylen Wong to run Open PDC on | Chad & Ethan | 2014-09-04 | Done |  |  | (Ask CPT Spruce for an RT Request)
| Complete Sprint Overview Video |  | 2014-09-11 | Done
| Write a work diary | Chad | 2014-09-09 | Done
| Create a preliminary network diagram | Chad | 2014-09-09 | Done
| Create 60 Elevator speech for video | Mike | 2014-09-09 | Done |  |  | Needs to include 5w's of the project and what we plan to do
| Coordinate with the EE majors to get their task list for our video | Ethan | 2014-09-09 | Done
| Create and initial set of user stories | Quentin | 2014-09-09 | Done
| x--NO LONGER NEEDED--x An article for local paper(pointer view) |  |  | Canceled | Canceled
| Learn more about Open PDC SQL formats and OS |  |  | Done | Can use mySQL or SQL Server. iPDC is on Linux, Open PDC for windows.
| Prioritize backlog & Finish sprint backlog | Ethan | 2014-09-09 | Done
Questions for Project Owner
| 1.Could PO put in a RT request for windows box? |  |  | Done | Doing it
| 2.What format does the user stories need to be in? |  |  | Done | Look at the lesson slides
| 3.What network specifications are there for the capstone? |  |  | Done | Likely no need for arouter but PO still doesn’t know
4.What criteria would the user look for/what will the user look for in the database?