## S#3PBL
Sprint 4 Back Log The Spruce Sprint "look at me. I am the Captain now." | Assigned? | Due Date? | Progress | Hours | Planned Hours | Notes Items increase in priority the higher they are in the list
PDR Presentation | ALL | 2014-11-12 |  | 4 | 4
Remake backlog | Ethan | 2014-10-24 | Done | 1 | 2 | Update PBL to account for new sprint (expected hours, addition of EE)
Do an official sync meeting with EE partners remake sprint goal | ALL | Immediately | Done | 7 | 7 | Get with EE partners and discuss everyone's needs and questions
Plan Sprint goal W/ CPT Spruce | ALL | 2014-10-31 | Done | 5 | 7 | Our orignal goal was changed to a much more tenacious one. Capture, store, and display was the new one.
Update GUI to EE partners' requests | Ethan+Quintin+Tim | 2014-10-30 |  | 2 | 2 | Fix the picture and the text boxes on the interface tab
Send commands to Open PDC to get data | Mike | 2014-11-14 |  | 5 | 4
Decode open PDC database | Mike | 2014-11-03 | Unsuccessful | 7 | 4 | Tried to find a database from OpenPDC of decipherable data… Ultimately failed…
Stand Ups across all work sessions | ALL |  |  | 6 | 6 | We're expecting this to be a lot higher because we have to coordinate with our EE partners
New Power World Diagram for GUI | Petar | 2014-11-06 |  | 2 | 3
Test DNS Server and Router | Chad | 2014-11-07 | Delayed | 0 | 3 | Chad says: No way to test, we need to request a router
Study how to control the grid from GUI | Quitin & Chad |  |  | 1 | 2
Intergroup lessons to decrease single points of failure | ALL |  |  | 3 | 4 | Q: Grid Chad: Networking Mike:OpenPDC Ethan:GUI/admin-X-
Research items we need to order | ALL | 2014-11-01 |  | 2 | 3 | (Chad & Quintin doing router requirements(MAJ Moses helped))
Determine design criteria | ALL |  |  | 2 | 3
Create GUI slides for powerpoint | Ethan | 2014-11-05 | Done | 3 | 1 | 4 slides provided for overall presentation
EE PDR updates | Tim, Petar, & Dan | 2014-11-12 | Done | 2 | 0 | Needed to update slides as per guidance from CPR Spruce.
Create design slides for PDR | ALL | 2014-11-12 |  | 6 | 5 | http://www-internal.eecs.usma.edu/courses/ee401/CapstoneDesignProject/ABET%20Outcome2%20Indicator2%20-%20EE401%20Preliminary%20Design%20Review.pdf
Enable GUI to create graphs and useful analysis | Ethan & Q |  |  | 0 | 3
Update the Power World Model | Dan |  |  | 2 | 2
Tutorials for the microcontrollers | Chad & Quintin | 2014-10-15 | In progress | 1 | 2 | The card that came with the microcontrollers shows the tutorials. Go meet with a teacher to get a better idea of VHDL
Edit PDR Slides | ALL | 2014-11-12 |  | 3 | 0
Networking for Grid | Chad & Quintin | 2014-11-05 |  | 2 | 0 | Although we were researching ways to connect the grid to the internet, we were told by our project owner that there would not be any internet connectivity
Plan Video for Sprint review | ALL | 2014-10-20 |  | 2 | 2 | Do a write up. Look at the notes in the notes app on Ethan's iPad, look at the slides from 10/7/14, and review notes from our grading rubrics
Film and edit Sprint 4 review | ALL | 2014-10-23 |  | 7 | 9 | Remember to charge the camera between takes. Again, refer to notes on Ethan's ipad for some tips
We will display accurate grid readings in our GUI, test and validate the Power World model and complete our PDR on 12 NOV. | Sprint Hours for IT & EE partners = 73.5 |  |  | 75 | 78
This column is now more of an indicator of what we orginally planned, not how long we expect each to take. A 0 means we didn’t expect it.

## Completed Items
Done
| Turn on the Grid and use Wireshark to view data |  | OTF | Complete | 4 | 0 | Wireshark has been capturing data but we've had some trouble capturing UDP packets
| Create relational schema | chad | 2014-10-04 | tentative | 1 |  | Chad created this but it doesn’t have the securoity information added yet
| Organize Wiring |  | 2014-10-04 |  |  |  | We rewired it to be better organized and work with out laptop better
| Order tripod for camera |  | 2014-10-04
| Build a provisional GUI in Visual Studio | Quintin & Ethan | 2014-10-04 |  | 2 |  | Gui is created on the desktop without any links to a database. It's really just a temporary design but hopefully we can transfer it over.
| Active Domain Preparation | Chad & Mike | 2014-09-11
| Create Network Diagram | Chad | 2014-09-11 | Done | 1
| Set up computer workstation and wiring | Ethan |  | Complete | 1
| Meet with the Test Bed Installers (Ask Questions) | ALL | 2014-09-11 | Complete | 8
| C# Refresher and practice using Ethan's old project | Quintin & Ethan | 2014-09-11 |  | 1 |  | Complete
| PLANNING & GOAL SETTING |  | 2014-10-04 |  | 4 | 8
| Smart Grid orientation | Quintin | 2014-10-04 |  |  | 2
| Plan sprint 2 video | ALL | 2014-10-04 |  |  | 2
| Build picture of grid for the GUI | Ethan | 2014-10-04
| Film video | ALL | 2014-10-04 |  |  | 2
| Finish Setting up Open PDC | Chad & Mike | 2014-10-04 | Installed | 3 | 1 | Installed but was delayed. We're having trouble working out the connection format of the open PDC to our PMUs
| Create a prototype GUI | Quintin & Ethan | 2014-10-04 | Completed on another computer | 5 | 3 | Install in progress but delayedbecuase of the computer delays
| Set Up DHCP | Chad & Mike | 2014-10-04 | On HDD | 0 | 3 | Install in progress but delayed
| Install SQLServer on our system | Quintin & Ethan | 2014-09-24 | Installed | 2 | 1 | Installed but was delayed. Compatibility issue with AGM version of windows used by USMA. We had to get a plan version of windows installed. Chad has been studying the functions of SQL server since its relatively new to all of us.
| Install Visual Studio on our system | Quintin & Ethan | 2014-09-26 | On HDD | 2 | 1 | Will Install but was delayed
| Write a work diary | Chad | 2014-09-09 | Done
| Create a preliminary network diagram | Chad | 2014-09-09 | Done
| Create 60 Elevator speech for video | Mike | 2014-09-09 | Done |  |  | Needs to include 5w's of the project and what we plan to do
| Coordinate with the EE majors to get their task list for our video | Ethan | 2014-09-09 | Done
| Create and initial set of user stories | Quentin | 2014-09-09 | Done
| x--NO LONGER NEEDED--x An article for local paper(pointer view) |  |  | Canceled | Canceled
| Learn more about Open PDC SQL formats and OS |  |  | Done | Can use mySQL or SQL Server. iPDC is on Linux, Open PDC for windows.
| Prioritize backlog & Finish sprint backlog | Ethan | 2014-09-09 | Done

## PO Questions
Questions for Project Owner
1.Could PO put in a RT request for windows box? | Done | Doing it
2.What format does the user stories need to be in? | Done | Look at the lesson slides
3.What network specifications are there for the capstone? | Done | Likely no need for arouter but PO still doesn’t know
4.What criteria would the user look for/what will the user look for in the database?