## S#3PBL
Sprint 3 Back Log The Honorary Dr. Mabry Sprint | Assigned? | Due Date | Progress | Hours | Planned Hours | Notes Items increase in priority the higher they are in the list
Finish install√ and create SQL Server Database | Chad & Mike | 2014-09-30 | Install done | 2 | 3 | The install process has blocked us from completing this in time. Chad has been studying it but hasn’t been able to get it ready
Connect the PMUs to Open PDC | Mike | 2014-10-23 | Done | 2 | 3 | Working on the networking and addressing with CPT Spruce
Re-vamp GUI on PDC machine | Ethan | 2014-10-19 | In Progress | 1 | 0 | We need to reformat the GUI because the old one had compatibility issues with the SQL database connection required.
Email Nick (The IT guy for the grid) | Mike | 2014-10-03 | Done | 1 | 1 | Got response emails from them. CPT Spruce forwarded them to all the group members.
Plan Sprint goal W/ CPT Spruce | ALL | 2014-09-17 | Done | 4 | 4 | Our orignal goal was changed to a much more tenacious one. Capture, store, and display was the new one.
Remake backlog | Ethan | 2014-10-04 | Done | 1 | 1 | Update PBL to the requirements shown by LTC Chewar
Make a new network chart | Chad | 2014-10-14 | Done | 2 | 2 | Making an updated chart to use when setting up DHCP
Locate the openPDC database | Mike | 2014-10-15 | Done | 1 | 2
Complete SQL Server database | Chad | 2014-10-15 | DONE | 2 | 2 | Once its installed correctly Chad can put his designs to work and follow the example of Dr. Mabry…
Tutorials for the microcontrollers | Chad & Quintin | 2014-10-15 | In progress | 2 | 0 | The card that came with the microcontrollers shows the tutorials. Go meet with a teacher to get a better idea of VHDL
Research new programming language for the solar connections | Quintin | 2014-10-15 | In progress | 5 | 3 | He's looking into the new language and formatting.
Connect OpenPDC to SQL Server | Mike & Chad | 2014-10-15 | Done | 3 | 3 | This was a lot easier than we expected. Open PDC has a default SQL server database that it writes to…
Update GUI to EE partners' requests | Ethan & Quintin | 2014-10-20 | Collecting ideas | 1 | 2 | Fix the picture and the text boxes on the interface tab
Set up history page on the GUI to browse | Ethan | 2014-10-23 | Done | 2 | 2 | I'm expecting it to be similar to what I had to do IOT finish my IT383 project.
Connect GUI to database | Ethan | 2014-10-20 | Done | 3 | 2 | Once we set up the database and load the GUI on the laptop I can get started
begin working with the Routing Protocol | Chad | 2014-10-04 | Done | 1 | 1 | We havent gotten to this since the computer issues have delayed us. Looking at installing a free version of MS Azure
Install Azure / Active Directory Lightweight System | Chad | 2014-10-15 | Doone | 2 | 2 | Azure is only for windows server or Windows 8 **scraped Azure and using Active Directory**
Get DHCP up and working | Chad | 2014-10-20 | DONE! | 3 | 3 | DHCP running but need a method to test it; was able to ping buses on grid. Still need to test if scope works
Program microcontollers for the solar portion | Quintin | 2014-10-23 | Researching | 0 | 0 | Still looking into the new programming language and working with Kazimer to get it functional
Plan Video for Sprint review | ALL | 2014-10-20 | In Progress | 1 | 1 | Do a write up. Look at the notes in the notes app on Ethan's iPad, look at the slides from 10/7/14, and review notes from our grading rubrics
Film and edit Sprint 3 review | ALL | 2014-10-23 | In Progress | 4 | 4 | Remember to charge the camera between takes. Again, refer to notes on Ethan's ipad for some tips | Make a write up of the things that were holding us up.
Set up DNS | Chad & Quintin MIKE |  |  | 2 | 0 | Need to get the documentation from LTC Robertson.
Do at least two official sync meetings with EE partners | ALL | 2014-10-25 |  | 1 | 3 | Get with EE partners and discuss everyone's needs and questions
Connect computer to PMU using AcSELerator Software | Chad | 2014-10-15 |  |  | 0 | Added by CPT Spruce
|  |  |  | 46 | 44
This column is now more of an indicator of what we orginally planned, not how long we expect each to take. A 0 means we didn’t expect it.
Sprint Hours = 42
Plan for 42 hours make it clear which thjings we're doing
Expected hours(instructor) and expected hours(team) need to be linked

## Completed Items
Done
| Turn on the Grid and use Wireshark to view data |  | OTF | Complete | 4 | 0 | Wireshark has been capturing data but we've had some trouble capturing UDP packets
| Create relational schema | chad | 2014-10-04 | tentative | 1 |  | Chad created this but it doesn’t have the securoity information added yet
| Organize Wiring |  | 2014-10-04 |  |  |  | We rewired it to be better organized and work with out laptop better
| Order tripod for camera |  | 2014-10-04
| Build a provisional GUI in Visual Studio | Quintin & Ethan | 2014-10-04 |  | 2 |  | Gui is created on the desktop without any links to a database. It's really just a temporary design but hopefully we can transfer it over.
| Active Domain Preparation | Chad & Mike | 2014-09-11
| Create Network Diagram | Chad | 2014-09-11 | Done | 1
| Set up computer workstation and wiring | Ethan |  | Complete | 1
| Meet with the Test Bed Installers (Ask Questions) | ALL | 2014-09-11 | Complete | 8
| C# Refresher and practice using Ethan's old project | Quintin & Ethan | 2014-09-11 |  | 1 |  | Complete
| PLANNING & GOAL SETTING |  | 2014-10-04 |  | 4 | 8
| Smart Grid orientation | Quintin | 2014-10-04 |  |  | 2
| Plan sprint 2 video | ALL | 2014-10-04 |  |  | 2
| Build picture of grid for the GUI | Ethan | 2014-10-04
| Film video | ALL | 2014-10-04 |  |  | 2
| Finish Setting up Open PDC | Chad & Mike | 2014-10-04 | Installed | 3 | 1 | Installed but was delayed. We're having trouble working out the connection format of the open PDC to our PMUs
| Create a prototype GUI | Quintin & Ethan | 2014-10-04 | Completed on another computer | 5 | 3 | Install in progress but delayedbecuase of the computer delays
| Set Up DHCP | Chad & Mike | 2014-10-04 | On HDD | 0 | 3 | Install in progress but delayed
| Install SQLServer on our system | Quintin & Ethan | 2014-09-24 | Installed | 2 | 1 | Installed but was delayed. Compatibility issue with AGM version of windows used by USMA. We had to get a plan version of windows installed. Chad has been studying the functions of SQL server since its relatively new to all of us.
| Install Visual Studio on our system | Quintin & Ethan | 2014-09-26 | On HDD | 2 | 1 | Will Install but was delayed
| Write a work diary | Chad | 2014-09-09 | Done
| Create a preliminary network diagram | Chad | 2014-09-09 | Done
| Create 60 Elevator speech for video | Mike | 2014-09-09 | Done |  |  | Needs to include 5w's of the project and what we plan to do
| Coordinate with the EE majors to get their task list for our video | Ethan | 2014-09-09 | Done
| Create and initial set of user stories | Quentin | 2014-09-09 | Done
| x--NO LONGER NEEDED--x An article for local paper(pointer view) |  |  | Canceled | Canceled
| Learn more about Open PDC SQL formats and OS |  |  | Done | Can use mySQL or SQL Server. iPDC is on Linux, Open PDC for windows.
| Prioritize backlog & Finish sprint backlog | Ethan | 2014-09-09 | Done

## PO Questions
Questions for Project Owner
1.Could PO put in a RT request for windows box? | Done | Doing it
2.What format does the user stories need to be in? | Done | Look at the lesson slides
3.What network specifications are there for the capstone? | Done | Likely no need for arouter but PO still doesn’t know
4.What criteria would the user look for/what will the user look for in the database?