## S#3PBL
Sprint 5 Back Log The Lanham Sprint* "Do push-ups" | Who? | When? | Progress | Hours | Planned Hours | Broken down tasks & Notes
Do an initial sync meeting with all partners | ALL | Immediately | Done | 7 | 7 | Get with EE partners and discuss everyone's needs and questions
Plan Sprint goal W/ CPT Spruce | ALL | 2014-11-20 |  | 5 | 7 | We will decode OpenPDC readings from the Smart Grid and update the GUI to display graphical representations of data.
Overhaul the GUI design to near implementation level | Ethan & Quintin + Tim | 2014-11-30 | Collecting ideas | 3 | 4 | Add click boxes to the picture, change colors, and clean it up
Study how to control the grid from GUI | Quintin, Ethan, and Petar | 2014-12-04 |  | 3 | 3
Research sending commands to OpenPDC | Ethan & Quintin | 2014-12-04 |  | 3 | 6 | Respond to the forum, we are using the coding sent by Stephen on the forum
Research decoding the database | Mike | 2014-11-26 |  | 3 | 6 | Posted questions on OpenPDC.complex and started to work on correcting the database
Enable GUI to create graphs and useful analysis | Ethan & Q | 2014-12-04 |  | 2 | 3
Reconfigure entire network (DHCP & DNS) | Chad | 2014-12-04 |  | 1 | 6 | The Server was completely wiped by the independent study cadet…CH…
Determine hardware for the server | Chad & Quintin | 2014-11-26 |  | 1 | 2 | Now that the server is taken by the independent study, we need to replan the hardware.
Cross train partners on areas of focus | ALL |  |  | 4 | 4
Simulation Matching to Testbed | Dan | 2014-11-26 |  | 4 | 4
Load profile design for testbed | Tim, Pete, Dan | 2014-12-04 |  | 5 | 6
Pseudocode algorithm for solar profile | Tim | 2014-12-04 |  | 3 | 8
Capacitor Profile Design for Test Bed | Pete | 2014-11-26 |  | 5 | 8 | Designed capacitor profile and met with advisors to verify. Changed plans and continued to meet to check for correctness
Standups throughout the sprint | ALL | 2014-11-27 |  | 5 | 5
Install ControlSuite | Quintin | 2014-12-02 |  | 1 | 0
Install Excel to view .csv readings from OpenPDC | Mike & Ethan | 2014-11-24 |  | 1 | 0
Connect computer to PMU using AcSELerator Software | Chad | 2014-11-26 |  | 1 | 3 | Added by CPT Spruce
Look over tutorials for the microcontrollers | Chad & Quintin | 2014-11-26 | In progress | 4 | 3 | The card that came with the microcontrollers shows the tutorials. Go meet with a teacher to get a better idea of VHDL
Research programming microcontollers for the solar portion | Quintin | Sprint 5 + | Researching | 4 | 3 | Still looking into the new programming language and working with Kazimer to get it functional
Attend AI for Microcontrollers | Quintin, Chad, Tim |  |  | 1 | 0
Design the web interface | Chad |  |  | 2 | 0 | General site design and template created.
NCUR Abstract | ALL EE | 2014-12-02 | Done | 2 | 0
Remake backlog | Ethan | 2014-11-18 | Done | 2 | 2 | Update PBL to account for new sprint (expected hours, addition of EE)
Plan Video for Sprint review | Ethan | 2014-12-05 |  | 2 | 2 | Do a write up. Look at the notes in the notes app on Ethan's iPad, look at the slides from 10/7/14, and review notes from our grading rubrics | Make a write up of the things that were holding us up.
Film and edit Sprint 5 review | ALL | 2014-12-08 |  | 1 | 9 | Remember to charge the camera between takes. Again, refer to notes on Ethan's ipad for some tips
Order Parts | ALL EE | 2014-12-02 |  | 8 | 0 | Had to find specific parts that meet all specifications/ meet with advisors to rebrief parts ordering plan. 8 hours specified bt CPT Spruce
Rebrief | ALL EE | 2014-12-02 | Done | 6 | 0
Group Firstie Club visit | ALL (even the EEs) | Every Thursday | Never ending | 0 | 0 | Turn down for spruce
*Featuring an Infantry blue back log. | Sprint Hours for IT & EE partners = 84 |  |  | 89 | 101
(was 100.8)

## Completed Items
Done
| Turn on the Grid and use Wireshark to view data |  | OTF | Complete | 4 | 0 | Wireshark has been capturing data but we've had some trouble capturing UDP packets
| Create relational schema | chad | 2014-10-04 | tentative | 1 |  | Chad created this but it doesn’t have the securoity information added yet
| Organize Wiring |  | 2014-10-04 |  |  |  | We rewired it to be better organized and work with out laptop better
| Order tripod for camera |  | 2014-10-04
| Build a provisional GUI in Visual Studio | Quintin & Ethan | 2014-10-04 |  | 2 |  | Gui is created on the desktop without any links to a database. It's really just a temporary design but hopefully we can transfer it over.
| Active Domain Preparation | Chad & Mike | 2014-09-11
| Create Network Diagram | Chad | 2014-09-11 | Done | 1
| Set up computer workstation and wiring | Ethan |  | Complete | 1
| Meet with the Test Bed Installers (Ask Questions) | ALL | 2014-09-11 | Complete | 8
| C# Refresher and practice using Ethan's old project | Quintin & Ethan | 2014-09-11 |  | 1 |  | Complete
| PLANNING & GOAL SETTING |  | 2014-10-04 |  | 4 | 8
| Smart Grid orientation | Quintin | 2014-10-04 |  |  | 2
| Plan sprint 2 video | ALL | 2014-10-04 |  |  | 2
| Build picture of grid for the GUI | Ethan | 2014-10-04
| Film video | ALL | 2014-10-04 |  |  | 2
| Finish Setting up Open PDC | Chad & Mike | 2014-10-04 | Installed | 3 | 1 | Installed but was delayed. We're having trouble working out the connection format of the open PDC to our PMUs
| Create a prototype GUI | Quintin & Ethan | 2014-10-04 | Completed on another computer | 5 | 3 | Install in progress but delayedbecuase of the computer delays
| Set Up DHCP | Chad & Mike | 2014-10-04 | On HDD | 0 | 3 | DELETED
| Install SQLServer on our system | Quintin & Ethan | 2014-09-24 | Installed | 2 | 1 | Installed but was delayed. Compatibility issue with AGM version of windows used by USMA. We had to get a plan version of windows installed. Chad has been studying the functions of SQL server since its relatively new to all of us.
| Install Visual Studio on our system | Quintin & Ethan | 2014-09-26 | On HDD | 2 | 1 | Will Install but was delayed
| Write a work diary | Chad | 2014-09-09 | Done
| Create a preliminary network diagram | Chad | 2014-09-09 | Done
| Create 60 Elevator speech for video | Mike | 2014-09-09 | Done |  |  | Needs to include 5w's of the project and what we plan to do
| Coordinate with the EE majors to get their task list for our video | Ethan | 2014-09-09 | Done
| Create and initial set of user stories | Quentin | 2014-09-09 | Done
| x--NO LONGER NEEDED--x An article for local paper(pointer view) |  |  | Canceled | Canceled
| Learn more about Open PDC SQL formats and OS |  |  | Done | Can use mySQL or SQL Server. iPDC is on Linux, Open PDC for windows.
| Prioritize backlog & Finish sprint backlog | Ethan | 2014-09-09 | Done

## PO Questions
Questions for Project Owner
1.Could PO put in a RT request for windows box? | Done | Doing it
2.What format does the user stories need to be in? | Done | Look at the lesson slides
3.What network specifications are there for the capstone? | Done | Likely no need for arouter but PO still doesn’t know
4.What criteria would the user look for/what will the user look for in the database?