## S#3PBL
Sprint 6 Back Log The Q Howard Jr. Sprint "WAMS" | Who? | Hours | Planned Hours | Broken down tasks & Notes
Do an initial sync meeting with all partners | ALL | 3 | 7 | Get with EE partners and discuss everyone's needs and questions (1 hour for each member)
Plan Sprint Goal | ALL | 3 | 7 | About 1 hour each, prepping ideas the night before then discussing. The goal has been planned!
Create a Query to limit entries sent to the GUI | Ethan and Mike | 5 | 4 | We finally got the query to work using the query builder then got it to stop crashing by not loading the entire database when the GUI started. Now we need to make the query load without us having to click it.
Get outside input for GUI design | Ethan | 0.5 | 2 | Ethan has only had the chance to talk to some cadets outside of our group and our advisors to get ideas so far.
Controll suite/microcontoller information | Quintin & Tim | 4 | 4 | We finally were able to download the necessary programs for ControlSuite and get the microcontroller connected to the program in order to begin setting up the variable (i.e. voltage, current, etc.) to match the grid
Test microcontoller connections | Quintin & Tim | 3 | 3 | Tim and CPT Spruce tested the inverter stage without grid connected and the full PV without grid connect
Determine Microcontoller connections | Quintin & Tim | 2 | 2 | We connected the microcontroller and board so that we can begin to test connections
Program Microcontrollers for grid | Quintin, Tim, & Chad | 4 | 4 | See items 6 and 7
Connect computer to PMU using AcSELerator Software | Chad and Mike | 0 | 2 | Will be completed in a later sprint after database and GUI taken care of
Work on Website Functions and Aesthetics | Chad and Ethan | 3 | 2 | Researched multiple ways to try and make site autonomous. Need to figure out file type to be used for historical data. Fixed various problems with aesthetics and website functionality.
Test TRIACs and ICs | Petar | 5 | 4
Simulate | Petar | 2 | 2 | Software issues. Moved on to testing actual Circuit
TestBed Testing | Daniel | 3 | 2 | Woring through functionality of SELs
Validate PowerWorld model with corrected grid | Tim and Daniel | 4 | 3 | Mostly Daniel's focus.
Configure ControlSuite program | Quintin | 3 | 2 | Q has been downloading and installing this, it has been a slow process since we all need the laptop. The downloads took longer than expected due to the size of the programs and the additional programs that were needed to run ControlSuite
PCB design | Tim, Daniel, and Petar | 0 | 2 | Have not started. Protoboard implementation will be used as a guideline for PCB implementation.
Testing parts (basic functionality tests) | ALL | 1 | 2 | Awaiting parts order. No failures!!
Reconfigure GUI | Ethan | 2 | 2 | GUI failure due to overwhelming size of SQL Server database. Removed the table associated with the database but GUI still continues to crash. Temporary GUI has been created to establish functionality with new configured PMU before aesthetics are applied.
Fix the scrumtop lock | Ethan | 2 | 0.5 | The laptop lock combo was lost and so Ethan went through ever possible combo and it still didn’t work. We just took apart the table it was locked to so its still locked but not attached to anything.
Use other computers to capture OpenPDC broadcast | ITs | 2 | 2 | We set Open PDC to broadcast the readings and we plan to use another computer to capture the broadcast and record the readings.
Review and edit OpenPDC data monitoring | Mike | 4 | 3 | Tried various adapters, historian settings, database settings, table creations, queries and PMU configurations. One PMU properly configured to send accurate and essential data to the database.
Study coding for real time display of data | Ethan | 2 | 2 | Use API http://openpdc.codeplex.com/wikipage?title=GEP%20Subscription%20Tester
Recreate the database on a smaller scale | Mike | 2 | 2 | Previous database was deleted from SQL Server and then remade. OpenPDC linked to new database and streamed only new, useful data sent by functioning PMU.
Determine meaning of Signal IDs | Mike | 2 | 2 | Worked with CPT Spruce and Dr. St-Leger to compare readings in database with readings on SEL units. Also discovered table of signal IDs within OpenPDC software that links ID string to specific reading from the Smart Grid | Make a write up of the things that were holding us up.
Prepare & Print CDR Brief slides | ALL | 5 | 4
Write CDR video/brief script | ALL | 3 | 4
Remake & update backlog | Ethan | 2 | 2 | SBL created for this sprint and new items added for the sprint goal.
Plan Video for Sprint review | Ethan | 1 | 1 | Do a write up. Review notes from our grading rubrics
Film and edit Sprint 6 review (CDR) | ALL | 3 | 3 | Remember to charge the camera between takes.
Implementation of design utilizing protoboard | Petar | 9 | 5 | The phasor action control board acts as the time dial for the solar panel. We had to program/get parts/test it.
Sprint Hours for IT & EE partners = 84 |  | 84.5 | 86.5 | Note: Mike was not present 1 session due to CGR tasking and Ethan was also not present 1 work session due to Gettysburg trip section for 2nd semester cadet leadership.
Translate and set parameters to filter data that is being sent to the GUI in order to graphically display data and develop a test plan that will allow us to validate with simulations and test all ordered parts to ensure they work as intended.

## Completed Items
Done
| Turn on the Grid and use Wireshark to view data |  | OTF | Complete | 4 | 0 | Wireshark has been capturing data but we've had some trouble capturing UDP packets
| Create relational schema | chad | 2014-10-04 | tentative | 1 |  | Chad created this but it doesn’t have the securoity information added yet
| Organize Wiring |  | 2014-10-04 |  |  |  | We rewired it to be better organized and work with out laptop better
| Order tripod for camera |  | 2014-10-04
| Build a provisional GUI in Visual Studio | Quintin & Ethan | 2014-10-04 |  | 2 |  | Gui is created on the desktop without any links to a database. It's really just a temporary design but hopefully we can transfer it over.
| Active Domain Preparation | Chad & Mike | 2014-09-11
| Create Network Diagram | Chad | 2014-09-11 | Done | 1
| Set up computer workstation and wiring | Ethan |  | Complete | 1
| Meet with the Test Bed Installers (Ask Questions) | ALL | 2014-09-11 | Complete | 8
| C# Refresher and practice using Ethan's old project | Quintin & Ethan | 2014-09-11 |  | 1 |  | Complete
| PLANNING & GOAL SETTING |  | 2014-10-04 |  | 4 | 8
| Smart Grid orientation | Quintin | 2014-10-04 |  |  | 2
| Plan sprint 2 video | ALL | 2014-10-04 |  |  | 2
| Build picture of grid for the GUI | Ethan | 2014-10-04
| Film video | ALL | 2014-10-04 |  |  | 2
| Finish Setting up Open PDC | Chad & Mike | 2014-10-04 | Installed | 3 | 1 | Installed but was delayed. We're having trouble working out the connection format of the open PDC to our PMUs
| Create a prototype GUI | Quintin & Ethan | 2014-10-04 | Completed on another computer | 5 | 3 | Install in progress but delayedbecuase of the computer delays
| Set Up DHCP | Chad & Mike | 2014-10-04 | On HDD | 0 | 3 | Install in progress but delayed
| Install SQLServer on our system | Quintin & Ethan | 2014-09-24 | Installed | 2 | 1 | Installed but was delayed. Compatibility issue with AGM version of windows used by USMA. We had to get a plan version of windows installed. Chad has been studying the functions of SQL server since its relatively new to all of us.
| Install Visual Studio on our system | Quintin & Ethan | 2014-09-26 | On HDD | 2 | 1 | Will Install but was delayed
| Write a work diary | Chad | 2014-09-09 | Done
| Create a preliminary network diagram | Chad | 2014-09-09 | Done
| Create 60 Elevator speech for video | Mike | 2014-09-09 | Done |  |  | Needs to include 5w's of the project and what we plan to do
| Coordinate with the EE majors to get their task list for our video | Ethan | 2014-09-09 | Done
| Create and initial set of user stories | Quentin | 2014-09-09 | Done
| x--NO LONGER NEEDED--x An article for local paper(pointer view) |  |  | Canceled | Canceled
| Learn more about Open PDC SQL formats and OS |  |  | Done | Can use mySQL or SQL Server. iPDC is on Linux, Open PDC for windows.
| Prioritize backlog & Finish sprint backlog | Ethan | 2014-09-09 | Done

## PO Questions
Questions for Project Owner
1.Could PO put in a RT request for windows box? | Done | Doing it
2.What format does the user stories need to be in? | Done | Look at the lesson slides
3.What network specifications are there for the capstone? | Done | Likely no need for arouter but PO still doesn’t know
4.What criteria would the user look for/what will the user look for in the database?