## S#3PBL
Sprint 7 Back Log The Chadwick Raiden Garcia Cortes sprint | Who? | Hours | Planned Hours | Broken down tasks & Notes
Sync meeting with all partners | ALL | 7 | 7 | Get with EE partners and discuss everyone's needs and questions (1 hour for each member)
Sync meeting with advisors | ALL | 7 | 7 | Get with advisors and discuss goals for Sprint and implementation
Plan Sprint Goal | ALL | 4 | 7 | Less than 1 hour total(each), prepping ideas the night before then discussing. The goal has been planned!
OpenPDC query to GUI query comparison and adding connections | Mike | 2 | 2 | Woking to add more connections to the GUI takes a lot of manual work time
R&D to reduce MS VS crashes and freezing | Mike | 3 | 2 | Reducing the amount of code and complicated factors to that have been making the gui crash.
Edit Sprint review video | Mike | 3 | 3 | Editing hours are estimated based on the editing time of the last 5 videos
Research adding graphical display to MS Visual Studio | Ethan | 2 | 1 | There arent any solid online resources for getting graphical display working… https://codeabout.wordpress.com/2011/05/15/easy-way-to-plot-graphs-in-c-and-visual-studio-2010/ https://www.youtube.com/watch?v=K31g-D7GaMM
Study how to change queries while running our GUI | Ethan | 3 | 3 | https://msdn.microsoft.com/en-us/library/ee256728.aspx http://opentsdb.net/docs/build/html/user_guide/guis/index.html
Allow the GUI to display a new form before the graphical display | Ethan & Mike | 2 | 2 | We're deliberating over th ebenefits of using new forms or just a tabulated system in one form. We've been testing both to see the performance differences and differences in functionality/aesthetics
Connecting our database queries to a MS VS graph | Ethan & Mike | 3 | 2 | Not a lot of resources for this…Ethan did find a good video though: https://www.youtube.com/watch?v=Hm_0ucMjRZY
Develop GUI display | Ethan & Mike | 5 | 6 | Work on the GUI display focusing on functionality over design
Testing and Implementing Python Script | Chad and Quintin | 5 | 4 | Able to read CSV files, write it to HTML code, and implement onto a website. Need to tailor to CPSG site.
Python Script Research | Chad & Quintin | 4 | 4 | They got some good input from MAJ A-M. The script will read the database csv file and write it to the HTML code.
Creating Python Script | Chad | 4 | 3 | Talked to MAJ Abbott-McCune about automatically pulling historical data from csv file to the website
Updating Website | Chad | 4 | 4 | Took the script from MAJ AM and tested website with it. Still working to successfully pull data
NCUR preparation | Tim, Quintin, and Petar | 5 | 5 | Prep for attending NCUR and the presentation
Testing Microcontrollers | Tim & Quintin | 6 | 5
Review code used in CodeComposer | Tim & Quintin | 4 | 4 | Microcontroller implementation was not moving according to schedule. Tim and Quintin reviewed the code to ensure that all variables were correctly input and
Finish testing capacitors, powerworld, etc. | EE partners | 4 | 4 | Tested Capacitors w/DME to determine C, Tested Inductors w/LRC Meter to determine L, tested inductors @multiple frequencies
PCB design | Tim, Daniel, and Petar | 4 | 4 | Design PCB using Ultiboard that will be used to implement the circuit with the grid (all three phases)
Power Factor Correction | Petar & Daniel | 5 | 5 | Designing circuit that corrects the power factor and testing/troubleshooting
Testing Phase Angle Controller Circuit w/ Load | Petar | 3 | 3 | Implementation of loads with previously built circuit and taking measurements
TRIAC noise filtering | Petar & Daniel | 2 | 2 | Filtering out noise from phase angle control circuit (failed/inductor filter too high)
Remake & update backlog | Ethan | 2 | 2 | SBL created for this sprint and new items added for the sprint goal.
Plan Video for Sprint review | Ethan | 1 | 1 | Do a write up. Review notes from our grading rubrics
Write CDR video/brief script | ALL | 2 | 2
Film Sprint 7 review | ALL | 4 | 4 | Remember to charge the camera between takes.
Get outside input for GUI design | Ethan | 1 | 2 | Talked to some other (Non EECS to get expectations)cadets to alter GUI design but its hasn’t been implemented
Connect computer to PMU using AcSELerator Software | Chad and Mike | 2 | 2 | Will be completed in a later sprint after database and GUI taken care of
Expected sprint hours = 100.8 = 6 work periods * 7 members * 80% effectiveness |  | 103 | 102 | Expectation of 14.4 hours per team member
We will graphically display data on the GUI, allow users to browse more historical data, enable data scripting on our website, and connect one microcontroller to the grid.
100.8