## S#3PBL
SGTB Sprint 8 Back Log The 1SG(ret.) Michael A. Finocchio sprint "You guys ever go skydiving? I Skydive!" | Who? | Hours | Planned Hours | Notes
Do an initial sync meeting with all partners & plan sprint goal | ALL | 7 | 7 | Get with EE partners and discuss everyone's needs and questions (1 hour for each member, one was absent)
Film Sprint 8 review (FDR) | ALL | 2 | 2 | Filiming for the FDR, much of it at individual times, probably more than 2 hours but hard to judge
Connect computer to PMU using AcSELerator Software | Mike, Quintin, Tim | 0 | 2 | Will be completed in a later sprint after database and GUI taken care of
Research on Python HTML scripting | Chad | 2 | 1 | Researched various methods to write data to HTML code. Looked into insert, replace, and other methods. Currently pursuing insert.
AI and coding of website | Chad | 4 | 2 | General performance and aesthetic fixes for the website as well as scripting compatibility.
Research into insert methods for script | Chad | 2 | 1 | Currently testing insert methods. Works on a small scale, trying to incorporate CSS and the entire site.
AI with MAJ Abbott McCune for site scripting | Chad and Quintin | 4 | 4 | AI helped us to initially write the Python script and understand what we needed to do to get data table written to website
AI with LTC Estes on python scripting website | Chad and Quintin | 2 | 2 | LTC Estes pointed us in the direction of various methods but suggested to hone into the insert method.
Independent research on AcSELerator | Quintin | 3 | 2 | Researched how to properly install and connect AcSELerator software to our laptops
Solar Microcontroller Inverter 26Vrms Grid Connection | Tim and Quintin | 3 | 4 | Finally able to connect to a 26 V grid WITHOUT any tranformers, Obsereved MPPT behavior, able to eliminate. Able to change current/power to grid.
Solar Microcontroller Inverter Code Debugging and manipulating | Tim and Quintin | 5 | 4 | Poured over the main code. Found discrepancies in literature, altered code to skip MPPT step that automatically enabled despite settings
AcSELerator Software connection to Relay | Tim and Quintin | 6 | 4 | Ethernet connection to Relay via telnet/TCP protocol
AcSELerator Software instalation and set up | Tim and Quintin | 2 | 4 | Installed and read literature on AcSELerator software and the SEL relays
Independent working on AcSELerator connection | Tim | 1 | 1 | Working throuhg literature and with Dr. St. Leger on establishing a connection
PCB design | Petar | 1 | 2 | PCB designed for a three phase load. Minor updates need to be changed (Pin 12 needs to be grounded)
Phase angle circuit with inductive load testing and troubleshooting | Petar | 9 | 5 | Designing the circuit, calculating values for different P.F., building the circuit for each P.F., measuring at 100%, 75%, 50%, 25%, working on digital control, troubleshooting
FDR Slides | Dan, Petar, Tim | 4.5 | 4 | Made presentation slides and practiced presentation 1.5hrs each
Capapcitor Bank PCB Design | Dan | 1 | 1 | Made the design for the PCB for the capacitor banks for power factor correction
Inductor Verification Testing | Dan | 1 | 1 | Verified the new inductors that were ordered to replace the ones that did not work.
Relay Switch Control | Dan | 1 | 1 | Determined how to control our relay switches so we can use them to switch on and off the Cap Banks
Controllable Load capabilities | Dan | 2 | 2 | Determined how to change pF of each individual load with a switch between caps and inductors on load & best figuration to do so
Integration Test Solution for Controllable Loads and Cap Banks | Dan | 2 | 2 | Came up with a test plan for how to integrate controllable load & Cap Banks into grid once enclosures are finished in ESG
Controllable Load Enclosure Design | Dan | 2.5 | 2 | Talked w/ESG and made an enclosure that can hold our controllable load and be able to dissipate heat put off from the resistors
Project's Day Abstract | Dan | 0.5 | 0 | Wrote an abstract for COL Shay to give to visitors for projects Day about CPSG | Make a write up of the things that were holding us up.
Create quadchart & deliverables | Ethan & Dan | 3 | 0 | Writing up the quard chart and making the write up for the FDR
Update and test User stories | Ethan | 1 | 3 | Have updated user stories for other cadets test |  | Ethan | 13 | 17
GUI prototyping and testing | Ethan | 2 | 3 | Running the GUI testing the query displays and functionality
Get outside input for GUI design | Ethan | 0 | 2 | Use other cadets to test our GUI design and functionality
Remake & update backlog | Ethan | 1.5 | 2 | SBL created for this sprint and new items added for the sprint goal.
Plan Video for Sprint review 8 | Ethan | 2 | 1 | Because of the added FDR guidance I had to edit the script and prepare a lot of entirely new information |  | Chad | 12 | 16
Research live updating and API use | Ethan & Mike | 2 | 3 | Sites: https://searchcode.com/codesearch/view/9906968/ http://http://stackoverflow.com/questions/5182824/execute-command-line-using-c-sharpstackoverflow.com/questions/5182824/execute-command-line-using-c-sharp http://stackoverflow.com/questions/3697299/passing-command-line-arguments-in-visual-studio-2010 |  | Mike | 12.5 | 17
Allow users to limit and filter the historical data | Ethan & Mike | 6 | 4 | We're trying to see about allowing the user to either edit the query and re-run it (ideal) or just filter the data. Sites used: https://msdn.microsoft.com/en-us/library/ms178306(v=vs.80).aspx
Transforming GUI into website format for future integration | Mike | 4.5 | 3 | Transforming the GUI on Visual Studio from small window application to full screen website that more closely models final product
Edit and finalize Sprint 8 video | Mike | 3.5 | 3 | Assemble and edit clips in Movie Maker and upload video to website |  | Q | 13 | 17
Trip to Indian Point Power Plant to become more familiar with real life load profiles | Petar | 0 | 4 | During our trip to Indian Point I focused on learning what some real load profiles look like in order to be able to simulate it better. |  | Dan | 13.5 | 17.5
Trip to Indian Point Power Plant to get hosted information experience | Chad | 0 | 4 | During our trip to Indian Point I focused on the interactions to hosted websites |  | Tim | 12.5 | 16.5
Trip to Indian Point Power Plant to Understand Advanced Metering and Relay Use | Tim | 0 | 4 | During our trip to Indian Point, I focused on learning how advanced metering and relay functionality is implimented from the geneation side of a Grid |  | Petar | 12.5 | 16.5
Trip to Indian Point Power Plant to understand hardware-software communication | Mike | 0 | 4 | During our trip to Indian Point, I focused on learning how the hardware and software components of the plant communicated with one another
Trip to Indian Point Power Plant to get Relay and PMU experience | Quintin | 0 | 4 | During our trip to Indian Point, I focused on researching the phaser measurement units and how they are controlled via relays
Trip to Indian Point Power Plant to Understand power generation/demand | Dan | 0 | 4 | During our trip to Indian Point, I focused on learning how they control the amount of power generated versus demand
Trip to Indian Point Power Plant to understand their GUI and interface design | Ethan | 0 | 4 | During our trip to Indian Point I focused on the professional GUI and interface designs used there as well as the GUI-Grid interactions
Sprint Hours for IT & EE partners = 84 |  | 93 | 112 | Hours expected per group member = 12 Without Trip section: 84 planned hours
Group Member Hours: Mike Finocchio: 13 ¦Ethan Gleue: 13 ¦Quintin Howard: 13 ¦Chad Cortes: 12 ¦Petar Repic: 12.5 ¦Dan Hawbaker: 13.5 ¦Tim Kazimer: 12.5 ¦
84
12

## Completed Items
Done
| Turn on the Grid and use Wireshark to view data |  | OTF | Complete | 4 | 0 | Wireshark has been capturing data but we've had some trouble capturing UDP packets
| Create relational schema | chad | 2014-10-04 | tentative | 1 |  | Chad created this but it doesn’t have the securoity information added yet
| Organize Wiring |  | 2014-10-04 |  |  |  | We rewired it to be better organized and work with out laptop better
| Order tripod for camera |  | 2014-10-04
| Build a provisional GUI in Visual Studio | Quintin & Ethan | 2014-10-04 |  | 2 |  | Gui is created on the desktop without any links to a database. It's really just a temporary design but hopefully we can transfer it over.
| Active Domain Preparation | Chad & Mike | 2014-09-11
| Create Network Diagram | Chad | 2014-09-11 | Done | 1
| Set up computer workstation and wiring | Ethan |  | Complete | 1
| Meet with the Test Bed Installers (Ask Questions) | ALL | 2014-09-11 | Complete | 8
| C# Refresher and practice using Ethan's old project | Quintin & Ethan | 2014-09-11 |  | 1 |  | Complete
| PLANNING & GOAL SETTING |  | 2014-10-04 |  | 4 | 8
| Smart Grid orientation | Quintin | 2014-10-04 |  |  | 2
| Plan sprint 2 video | ALL | 2014-10-04 |  |  | 2
| Build picture of grid for the GUI | Ethan | 2014-10-04
| Film video | ALL | 2014-10-04 |  |  | 2
| Finish Setting up Open PDC | Chad & Mike | 2014-10-04 | Installed | 3 | 1 | Installed but was delayed. We're having trouble working out the connection format of the open PDC to our PMUs
| Create a prototype GUI | Quintin & Ethan | 2014-10-04 | Completed on another computer | 5 | 3 | Install in progress but delayedbecuase of the computer delays
| Set Up DHCP | Chad & Mike | 2014-10-04 | On HDD | 0 | 3 | Install in progress but delayed
| Install SQLServer on our system | Quintin & Ethan | 2014-09-24 | Installed | 2 | 1 | Installed but was delayed. Compatibility issue with AGM version of windows used by USMA. We had to get a plan version of windows installed. Chad has been studying the functions of SQL server since its relatively new to all of us.
| Install Visual Studio on our system | Quintin & Ethan | 2014-09-26 | On HDD | 2 | 1 | Will Install but was delayed
| Write a work diary | Chad | 2014-09-09 | Done
| Create a preliminary network diagram | Chad | 2014-09-09 | Done
| Create 60 Elevator speech for video | Mike | 2014-09-09 | Done |  |  | Needs to include 5w's of the project and what we plan to do
| Coordinate with the EE majors to get their task list for our video | Ethan | 2014-09-09 | Done
| Create and initial set of user stories | Quentin | 2014-09-09 | Done
| x--NO LONGER NEEDED--x An article for local paper(pointer view) |  |  | Canceled | Canceled
| Learn more about Open PDC SQL formats and OS |  |  | Done | Can use mySQL or SQL Server. iPDC is on Linux, Open PDC for windows.
| Prioritize backlog & Finish sprint backlog | Ethan | 2014-09-09 | Done

## PO Questions
Questions for Project Owner
1.Could PO put in a RT request for windows box? | Done | Doing it
2.What format does the user stories need to be in? | Done | Look at the lesson slides
3.What network specifications are there for the capstone? | Done | Likely no need for arouter but PO still doesn’t know
4.What criteria would the user look for/what will the user look for in the database?