## S#3PBL
Sprint 9 Back Log The CSM Ethan Gleue Sprint "Chad! Get off your iPad" | Who? | Hours | Planned Hours | Broken down tasks & Notes
Do an initial sync meeting with all partners & plan sprint goal | ALL | 7 | 7 | Get with EE partners and discuss everyone's needs and questions (1 hour for each member, one was absent)
Porject Day Planning | All | 7 | 7 | Worked to get finished this during weekend. Creating Script for Project's Day and the plan for the video compilation
Film Sprint 9 review (Prototype Demo)/Presentation prep | ALL | 14 | 10 | prepping for the Prototype Demo, much of it at individuallly, probably more than 2 hours but hard to judge
Data script preparation | Chad and Quintin | 4 | 4
Script testing and 'insert' method troubleshooting | Chad | 2 | 2 | Troubleshooting 'insert' method, had trouble defining the proper line inserts and counters. LTC Lanham helped troubleshoot the script's line count.
Website cleanup/finalization | Chad and Quintin | 4 | 4 | Creating working website with little to no bugs
Research pagination for script | Quintin | 2 | 2 | Researched pagination for the woebsite ***Did not use pagination mathods***
Seek AI for website script | Chad and Quintin | 4 | 4 | Received AI for website script from LTC Estes, MAJ Abbott-McCune, and LTC Martin
NCUR preparation (poster board, working knowledge, presentation skills, etc.) | Petar, Quintin, Tim | 3 | 3 | NCUR (15 April)
Prep deliverables for turnin in my absence | Ethan | 1 | 1 | Prepping backlog, script, filming, and deliverables.
| Ethan | 1 | 1 | Edits from FDR and corrections
Remake & update backlog/ admin work | Ethan | 4 | 2 | SBL created for this sprint and new items added for the sprint goal. Created sprint eval sheets, organized and printed necessary rubric sheets and planned team work up to the end of the sprint to plan fo success.
Plan Video for Sprint review 9 | Ethan | 1 | 1 | Because of the added FDR guidance I had to edit the script and prepare a lot of entirely new information
GUI Sprint 9 eval and testing | Ethan and Mike | 2 | 2 | Cataloging progress with GUI and evaluating what to do next
Edit and finalize Sprint 9 video | Mike | 3 | 3 | Assemble and edit clips in Movie Maker and upload video to website
Complete Query Builder | Mike | 4 | 3 | Coding the query builder to allow the user to pick from a few options. We hard coded it for the sake of operability with our limited time.
Control Circuit PCB | Petar | 6 | 4 | Revise, troubleshoot, build and test the PCB for Control Circuit
Build the neutral bus | Petar, Tim | 2 | 2 | Building the neutral bus that will be used for control circuit
Connect computer to PMU using AcSELerator Software | Mike, Quintin, Tim | 3 | 3 | Will be completed in a later sprint after database and GUI taken care of
Ensure connectivity from SEL properly working | Mike, Quintin, Tim | 3 | 2 | After installing AcSELerator program on computer, ensuring that breakers can be controlled from the laptop
Wiring Solar To Grid | Tim | 2 | 2 | Making proper connections with our specific connection types
Re working Solar Code With Advisors | Tim | 1 | 1 | Trying to change the PV Current draw start point, reset code to what it was before
Testing Solar Inverter Microcontroller on the Grid | Tim, Petar | 3 | 2 | Changing current draw on grid, observing results
Design Posterboard for projects day | Tim, Dan, Ethan | 3 | 4 | Creating the tenative design for the posterboard presentation. 25 MAR
Build the load enclosure and soldered connections | Daniel, Petar | 4 | 4 | Screwed in the Inductors and resistors to enclosure. Soldered connections for Cap PCB, and connections between resistors, inductors and the connectors to put on grid. 3hrs Dan. 1hr Petar
Making User Manual | Daniel, Tim | 3 | 3 | Tim and Daniel wrote the user manual to describe the different parts of the test bed and describe how to use the test bed. 2hrs Dan, 1hr Tim
Testing Load on Grid w/Solar Input & Cap Banks | Daniel | 2 | 2 | Attached the inductive load to the grid and made sure it connected properly and caused a phase angle shift. Added solar input on one phase to help w/power draw for load. Tested turning on cap banks on grid to counteract phase angle shift from inductors
Working on Control of Switching Relays w/SELs | Daniel | 1.5 | 2 | Looked into how the current relays work w/Control signals from SELs. Determined not enough time to complete, changed to manual switches for turning on loads and Cap Banks. Need a control circuit w/transistor on top of relays to take signals from SELs to turn on or off
Sprint Hours for IT & EE partners = 84 Hours (12 hours each) |  | 96.5 | 87
Group Member Hours: Mike Finocchio: 14 ¦Ethan Gleue: 13 ¦Quintin Howard: 15 ¦Chad Cortes: 12 ¦Petar Repic: 14.5 ¦Dan Hawbaker:13.5 ¦Tim Kazimer: 14.5 ¦
During sprint 9 we will research how to display multiple readings from open PDC to our GUI, prototype our GUI interface, enable our website to script data onto html pages, and control the grid remotely from our laptop.

## Completed Items
Done
| Turn on the Grid and use Wireshark to view data |  | OTF | Complete | 4 | 0 | Wireshark has been capturing data but we've had some trouble capturing UDP packets
| Create relational schema | chad | 2014-10-04 | tentative | 1 |  | Chad created this but it doesn’t have the securoity information added yet
| Organize Wiring |  | 2014-10-04 |  |  |  | We rewired it to be better organized and work with out laptop better
| Order tripod for camera |  | 2014-10-04
| Build a provisional GUI in Visual Studio | Quintin & Ethan | 2014-10-04 |  | 2 |  | Gui is created on the desktop without any links to a database. It's really just a temporary design but hopefully we can transfer it over.
| Active Domain Preparation | Chad & Mike | 2014-09-11
| Create Network Diagram | Chad | 2014-09-11 | Done | 1
| Set up computer workstation and wiring | Ethan |  | Complete | 1
| Meet with the Test Bed Installers (Ask Questions) | ALL | 2014-09-11 | Complete | 8
| C# Refresher and practice using Ethan's old project | Quintin & Ethan | 2014-09-11 |  | 1 |  | Complete
| PLANNING & GOAL SETTING |  | 2014-10-04 |  | 4 | 8
| Smart Grid orientation | Quintin | 2014-10-04 |  |  | 2
| Plan sprint 2 video | ALL | 2014-10-04 |  |  | 2
| Build picture of grid for the GUI | Ethan | 2014-10-04
| Film video | ALL | 2014-10-04 |  |  | 2
| Finish Setting up Open PDC | Chad & Mike | 2014-10-04 | Installed | 3 | 1 | Installed but was delayed. We're having trouble working out the connection format of the open PDC to our PMUs
| Create a prototype GUI | Quintin & Ethan | 2014-10-04 | Completed on another computer | 5 | 3 | Install in progress but delayedbecuase of the computer delays
| Set Up DHCP | Chad & Mike | 2014-10-04 | On HDD | 0 | 3 | Install in progress but delayed
| Install SQLServer on our system | Quintin & Ethan | 2014-09-24 | Installed | 2 | 1 | Installed but was delayed. Compatibility issue with AGM version of windows used by USMA. We had to get a plan version of windows installed. Chad has been studying the functions of SQL server since its relatively new to all of us.
| Install Visual Studio on our system | Quintin & Ethan | 2014-09-26 | On HDD | 2 | 1 | Will Install but was delayed
| Write a work diary | Chad | 2014-09-09 | Done
| Create a preliminary network diagram | Chad | 2014-09-09 | Done
| Create 60 Elevator speech for video | Mike | 2014-09-09 | Done |  |  | Needs to include 5w's of the project and what we plan to do
| Coordinate with the EE majors to get their task list for our video | Ethan | 2014-09-09 | Done
| Create and initial set of user stories | Quentin | 2014-09-09 | Done
| x--NO LONGER NEEDED--x An article for local paper(pointer view) |  |  | Canceled | Canceled
| Learn more about Open PDC SQL formats and OS |  |  | Done | Can use mySQL or SQL Server. iPDC is on Linux, Open PDC for windows.
| Prioritize backlog & Finish sprint backlog | Ethan | 2014-09-09 | Done

## PO Questions
Questions for Project Owner
1.Could PO put in a RT request for windows box? | Done | Doing it
2.What format does the user stories need to be in? | Done | Look at the lesson slides
3.What network specifications are there for the capstone? | Done | Likely no need for arouter but PO still doesn’t know
4.What criteria would the user look for/what will the user look for in the database?

## Sheet1
Expected sprint hours = 100.8= 5 work periods * 7 members *3 hours* 80% effectiveness
84
12